## Sheet1
|  | Professsional |  |  |  | Institutional
| Self - Patient |  | Dependent |  | Self - Patient |  | Dependent
Platform | Paper | Electronic | Paper | Electronic | Paper | Electronic | Paper | Electronic | Total Test Data Requested | Total Test Data Provided | Test Data Validated on Claims HWY Bravo | Claims HWY Validation on table (Adj and Pre-Adj) | Pega Validation | ALM Ticket | NOTES
Cosmos | 16 | 17 | 8 | 8 | 12 | 14 | 4 | 8 | 75 | 87 | 87 | 87 | Validated a handful of scenario's and working | 766 | Currently got 4 test data for each scenarios. Need 5 for each --> 40 at least 10/18: Received additional test data. TIna/Satish to review and share. 10/20 : Piyush to verify data received. 10/24: have a claims with >50 lines(professional/electronic); 10/24: received ICD9 test data (7 claims)
Nice | 25 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 75 | 29 | 29 | 9 confirmed. ALM pending to validate the 20 | Issues - B2B: Pending working session | 1873 | Missing some info - 10/18: Expect to hear back tomorrow since they are offshore. 10/19: Satish to provide update EOD. 10/20: Claims Bravo is good. Needs validation against adjudication table. 10/21: Will be providing more test data (mid next week?) 10/25: confirmation received, more to come
Unet/Tops | 21 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 75 | 31 | 31 | Pending ALM |  | 1724 | Missing TIN info - 10/18: Expect to hear back tomorrow since they are offshore 10/19: Satish to provide update EOD. 10/20: Claims Bravo is good. Needs validation against adjudication table. Sharon has a mtg with CQA to assist Satish on the test data. 10/21: More to come by EOD or Monday 10/25: confirmed email on additional data
CSP/Facets | [14 empty] | Pending contact - 10/18: has been escalated. 10/21: Richard continue to follow up. 10/25: More to know today and meeting on Thursday
Pega Stage --> B2B Prod
Pega Dev/Test --> B2B Bravo
Validated/Received/Requested Claims
Currently got 4 test data for each scenarios. Need 5 for each --> 40 at least